## Sheet1
Election: | Renhold Parish North Ward By-Election - Thursday 18th August 2022
Venue: | Renhold Village Hall
Stations: | 1
Event | Date | Comments
Publication of notice of election | Thursday 14 July
Dispatch of Poll Cards | Between Thursday 14 to Monday 18 July
Delivery of nomination papers | Friday 15 to Friday 22 July | CC to process nominations
Deadline for withdrawals of nomination | Friday 22 July
Publication of first interim election notice of alteration | Friday 22 July
Publication of statement of persons nominated | Monday 25 July
1st Postal Vote dispatch | Friday 29 July | Monday 25 July upload data
Deadline for receiving applications for registration | Tuesday 2 August
Publication of second interim election notice of alteration | Wednesday 10 August
Deadline for receiving new postal vote and postal proxy applications, and for changes to existing postal or proxy votes | Wednesday 3 August
Deadline for receiving new applications to vote by proxy (not postal proxy or emergency proxies) | Wednesday 10 August
Publication of notice of poll and situation of polling stations | Wednesday 10 August
Publication of final election notice of alteration | Thursday 11 August
Deadline for notification of appointment of polling and counting agents | Thursday 11 August
2nd issue Postal Vote dispatch | Thursday 11 August
2nd issue Proxy poll card dispatch (if required) | Thursday 11 August
First date that electors can apply for replacements for lost postal votes | Friday 12 August
Delivery of ballot papers, spare pv packs etc to Borough Hall | Thursday 11 August
Virtual briefing session | N/A | N/A
Delivery of polling booth | Wednesday 9 August | LB
Filling and collection of Ballot Box | Tuesday 16 August | Time tbc
Polling day | Thursday 18 August
Opening of postal votes | Thursday 18 August | CC and CG to open at BH in the pm
Last time that electors can apply for a replacement for spoilt or lost postal votes | Thursday 18 August 5pm
Deadline for emergency proxy applications | Thursday 18 August 5pm
Last time to alter the register due to clerical error or court appeal | Thursday 18 August 9pm
Delivery of return as to election expenses (parish council elections only) | Thursday 22 September
Deadline for sending postal vote identifier rejection notices | Thursday 29 September